| Name of Sponsor: IRCCS OSPEDALE SAN RAFFAELE |  | Statement on discontinuation of the study |  |
| --- | --- | --- | --- |
| Investigational Product: Donepezil |  | EudraCT No.: 2008-001940-38 |  |
|  |  | Page: 1 |  |
| Report Date: 17/04/2025 | Trial No.: RMFD5-10 | Dates of Trial: 22/04/2008-23/05/2012 |  |
| Title of Trial: | Functional Magnetic Resonance study to evaluate the prompt and middle term effect of the treatment with Donepezil in patients affected by multiple sclerosis and mild impairment of cognitive function. |  |  |
| Trial Sites: | IRCCS Ospedale San Raffaele |  |  |
| Publications: | NA |  |  |
| Clinical Phase: | Phase II |  |  |
| Statement on discontinuation of the study: | The trial was authorized on April 22, 2008, with the first patient enrolled on October 4, 2008. The study concluded on May 23, 2012 (last patient last visit). A total of 11 multiple sclerosis (MS) patients and 2 healthy controls were enrolled. Out of the 11 patients, 8 completed the protocol, while 3 were drop-outs. Cause of drop-out for the first patient was sweating, chills, general sense of discomfort, and blurred vision approximately two hours after donepezil administration, with elevated creatine phosphokinase levels in the blood. The second patient decided to withdraw from the study due to nausea/general discomfort after donepezil administration and excessive magnetic resonance protocol duration. The third patient dropped out not due to adverse events but due to a clinical relapse of MS disease. The trial was prematurely interrupted because of the scarcity of MS patients with eligible inclusion criteria for enrollment in the study, which made not possible to complete recruitment. A total of 40 MRI scans were performed for this study: 32 scans from the 8 patients who completed the study, 6 scans from the three dropout patients, and 2 scans from the two enrolled healthy controls. Each of these exams was analyzed at the single-subject level, including lesion load and brain volume estimation, as well as first-level activation analyses of the functional MRI tasks performed by the subjects (simple hand motor task, N-back and face encoding tasks). However, due to the premature interruption of the study, second-level statistical analyses were not conducted because of insufficient sample size. |  |  |