Notification of early termination

EudraCT Number: 2010-022075-66

Title of Study: A Single Centre Physiological Study of Glucose Metabolism Before and After Tacrolimus Withdrawal For Deteriorating Kidney Function In Renal Transplant Recipients

Name of Sponsor: Cardiff and Vale University Health Board

Name of CI: Dr Argiris Asderakis

Date 07/06/2022

Results cannot be provided as this trial never started. The end of trial declaration form stated “The justification for early termination of the trial; In the 9 months since the Trial has been open to recruitment, the Research team have only succeeded in recruiting 1 subject, due to the clinical care preferences of the medical team resulting in a lower subject eligibility than was first thought. The subject was recruited, and attended a screening visit, but subsequently became ineligible to proceed further in the Trial, due to a change in his clinical care plan. The co- investigator is soon to take up post elsewhere, and will not be replaced, which will leave insufficient staff to proceed with the Trial. Therefore, the decision was taken to terminate this Trial earlier than expected. Although this Trial has terminated with no results, The Investigators have learned a valuable lesson in Protocol design, which includes more careful consideration to the inclusion/exclusion criteria and patient suitability”