Odense March 21, 2025

Project title:

Recurrent and Metastatic Prostate Cancer: Impact of 18F-PSMA-1007 PET/CT on clinical decision making and response monitoring (REPRISMA)

EudraCT number: 2021-000184-78

Competent authority registration number: Journal 2021051003 (approval given by “Danish Health and Medicines Autority”)

Danish Ethics committee registration number: VEK ID: S-20190080

Sponsor Organization (single center):

Odense University Hospital

Att. Malene G. Hildebrandt

Department of Nuclear Medicine

Kloevervaenget 47

5000 Odense C

Denmark

Sponsor’s protocol code number: 2020110470

The reason for early end of trial on May 1 2024 was mainly lack of recruitment of participants/patients. Partly because patients were reluctant to repeatedly come twice for scans for a period of two years, and partly because the guidelines for treatment changed during inclusion period (in 2023), which made it hard for clinicians to find patients to fit the inclusion criteria of the project, and they gave up looking for suitable candidates. We only managed to include two patients. The number of patients still receiving treatment at time of early termination in the MS concerned by the declaration and their proposed management (the PSMA radiotracer) is zero.

There were no adverse events to the PSMA given in the project. The consequences of early termination for the evaluation of the results and the investigational medicinal product we estimate the risk to be infinitely small for the PSMA as a medicinal product, because PSMA is already given in everyday clinical settings all over the world scanning prostate cancer patients with PSMA-PET/CT, and with no known adverse events. This project was performed as a clinical trial only because PSMA tracer was used in a research setting in this project.

Because of the restricted number of patients and scans, we achieved no usable results, and hence did not publish any results from this clinical study.